## Sheet1
Annex 3. Demonstration Workplan
Title of the Demonstration Project:
Activity No. | Activity Title | Description of Activity | Expected Deliverables | Responsible Party | Start Date | End Date | Location | Indicators / Monitoring Means
1 | /SAMPLE/ Project Kick-off & Team Mobilization | /SAMPLE/ Recruitment of staff, confirmation of co-financing, procurement planning, partnership confirmation | /SAMPLE/ Kick-off meeting report, signed MoUs or subcontracts, project team in place | /SAMPLE/ Applicant + Partners | dd/mm/yyyy | dd/mm/yyyy | /SAMPLE/ [City/Village, Region] | /SAMPLE/ Meeting minutes, contracts, time sheets
2 | /SAMPLE/ Sustainable Packaging Design & Prototyping | /SAMPLE/ Development and prototyping of recyclable, biodegradable, or agro-waste-based packaging | /SAMPLE/ Tested packaging prototype; design documentation | /SAMPLE/ Technical Team / Packaging Expert | dd/mm/yyyy | dd/mm/yyyy | /SAMPLE/ Laboratory / Workshop | /SAMPLE/ Prototype samples, test reports
3 | … | … | … | … | dd/mm/yyyy | dd/mm/yyyy | … | …
4 | … | … | … | … | … | … | … | …
5 | … | … | … | … | dd/mm/yyyy | dd/mm/yyyy | … | …